# SoleFinder — Agile & DevOps Practices: Final Lab Documentation

Full name: Fabrice Sheja

Specialization: Data Engineering

Date: 10 October 2026

GitHub repository: https://github.com/kelvee21/solefinder

Jira board: https://amali-tech.atlassian.net/jira/software/projects/AGILE/boards/5600

# 1. Product vision

SoleFinder helps small shoe merchants sell online: merchants register and list their shoes, and customers can browse the catalog and search by brand.

# 2. Product backlog

Points are relative (merchant registration = 5 points). Highest priority first.

| Key | Story | Epic | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- |
| AGILE-8 | Set up CI pipeline with GitHub Actions | Platform & Operations | Highest | 2 | Sprint 1 |
| AGILE-9 | As a merchant, I can register so I can sell shoes | Merchant Management | Highest | 5 | Sprint 1 |
| AGILE-10 | As a merchant, I can add a shoe to my inventory | Merchant Management | Highest | 3 | Sprint 2 |
| AGILE-11 | As a customer, I can browse all shoes | Customer Experience | High | 2 | Sprint 2 |
| AGILE-12 | As a customer, I can search shoes by brand | Customer Experience | High | 2 | Backlog |
| AGILE-13 | As a merchant, I can update stock/price or delete a shoe | Merchant Management | Medium | 5 | Backlog |
| AGILE-14 | As a customer, I can register | Customer Experience | Medium | 3 | Backlog |
| AGILE-15 | As an operator, I can check a health endpoint | Platform & Operations | Medium | 2 | Sprint 2 |
| AGILE-16 | As a customer, I can add shoes to a cart | Customer Experience | Low | 5 | Backlog |
| AGILE-17 | As a customer, I can find similar shoes by image (simulated) | Future Ideas (Icebox) | Low | 8 | Backlog |

# 3. Acceptance criteria (delivered stories)

AGILE-8: every push runs the pipeline; install + tests pass on a clean runner.

AGILE-9: POST /merchants returns 201 with id, name and email; bad email and blank name return 422.

AGILE-10: POST /shoes returns 201 with id, brand, model and price; blank brand/model and non-positive price return 422.

AGILE-11: GET /shoes returns all added shoes; empty catalog returns [].

AGILE-15: GET /health returns 200 {"status": "ok"}; each endpoint prints a console log line per request.

# 4. Definition of Done

Code on the sprint branch and acceptance criteria met.

Unit/integration tests written and passing (pytest).

CI pipeline green on the pushed branch.

No junk files committed (__pycache__, .coverage, secrets).

Jira story moved to Done with test/CI evidence linked.

# 5. Sprint 1 — plan, review, retrospective

## Plan

Goal: prove we can deliver tested code with CI on every push. Selected AGILE-8 (2 pts) + AGILE-9 (5 pts) = 7 points. The CI task came first so every later story is tested automatically.

## Review

Delivered 7/7 points: CI pipeline (branch feature/AGILE-8-ci-pipeline) and merchant registration (branch feature/AGILE-9-merchant-registration). Demo: POST /merchants {"name": "Foot Locker", "email": "a@shop.com"} -> 201; bad email -> 422. 5 tests passed, CI green.

## Retrospective

What went well: small commits made failures easy to locate; tests caught real bugs; the pipeline runs in under a minute.

What went badly: (1) the first three CI runs failed — pytest could not import the app package on the runner; (2) the smoke test failed because app/main.py was still empty on that branch; (3) no visibility when something failed — no health check, no request logs.

Improvements for Sprint 2: (1) fixed CI imports with pyproject.toml and verify with the exact CI command locally; (2) scaffold the app in the same story as its smoke test; (3) add GET /health plus console logs (AGILE-15).

# 6. Sprint 2 — plan, review, retrospective

## Plan

Goal: grow the catalog and make the service observable. Selected AGILE-10 (3 pts) + AGILE-11 (2 pts) + AGILE-15 (2 pts) = 7 points. AGILE-15 was pulled ahead of AGILE-12/13/14 because this sprint requires monitoring/logging.

## Review

Delivered 7/7 points on stacked branches feature/AGILE-10-add-shoe -> feature/AGILE-11-browse-shoes -> feature/AGILE-15-health-endpoint. Demo: POST /shoes -> 201; GET /shoes -> list; GET /health -> 200 {"status": "ok"}; console shows one log line per request. 11 tests pass, 100% coverage. All three Sprint 1 retro improvements were applied; CI was green on the first try every time.

## Retrospective

What went well: CI green first try on all branches; small commits (schema, schemas, endpoint, tests); the reset_db fixture worked unchanged for shoes. What went badly: logging meant editing every endpoint by hand (a central place would be better next time); the pytest config first broke on the older branch layout (fixed as layout-agnostic). Next: AGILE-12 search, then AGILE-13 update/delete.

# 7. CI/CD evidence

Pipeline .github/workflows/ci.yml runs on every push and pull request: checkout, Python 3.12 with pip cache, pip install, python -m pytest --cov=app --cov-report=term. All runs below are green with every step successful (full step list verified via the Actions API).

Run #10 (feature/AGILE-8-ci-pipeline, commit f877861): success — https://github.com/kelvee21/solefinder/actions/runs/38067675736

Run #11 (feature/AGILE-9-merchant-registration, commit faae11b): success — https://github.com/kelvee21/solefinder/actions/runs/38067676495

Run #13 (feature/AGILE-10-add-shoe, commit a5ef1c9): success — https://github.com/kelvee21/solefinder/actions/runs/38070007077

Run #14 (feature/AGILE-11-browse-shoes, commit 05976b8): success — https://github.com/kelvee21/solefinder/actions/runs/38070139437

Run #15 (feature/AGILE-15-health-endpoint, commit 5f77e2c): success — https://github.com/kelvee21/solefinder/actions/runs/38070254452

# 8. Testing evidence

Command: python -m pytest --cov=app --cov-report=term. Result: 11 passed, 100% coverage on app code. Tests: 1 smoke (app loads), 4 merchant (register 201; invalid email, blank name, blank email -> 422), 5 shoe (add 201; blank brand, bad price -> 422; list returns added shoes; empty catalog -> []), 1 health (200 {"status": "ok"}). Each test uses a fresh database via the autouse fresh_db fixture (reset_db before every test), so ids restart at 1 and tests never affect each other.

app\__init__.py        0      0   100%

app\database.py       18      0   100%

app\db\__init__.py    0      0   100%

app\db\schemas.py    12      0   100%

app\main.py           29      0   100%

TOTAL                  118      0   100%

11 passed in 0.72s

# 9. Repository and how to run

Branches: main; feature/AGILE-8-ci-pipeline; feature/AGILE-9-merchant-registration; feature/AGILE-10-add-shoe; feature/AGILE-11-browse-shoes; feature/AGILE-15-health-endpoint (stacked, each story in small commits).

Tests: python -m pytest --cov=app --cov-report=term

Run the app: uvicorn app.main:app, then open http://localhost:8000/health

Jira: AGILE project, Sprint 1 (Oct 5-12, closed) and Sprint 2 (Oct 10-17, closed); stories moved To Do -> In Progress -> In Review -> Done with commit and CI-run links in comments.